## Traditional_Logs
Phase | Sub-task | Role | StartTime | EndTime | Hours | Description
Requirement Analysis | Manual requirements interpretation | Project Manager | 2024-04-01 09:20 | 2024-04-01 10:32 | 1.2 | Review seafood traceability brief and draft user stories for Fisher/Retailer; coordinate/review (log 1)
Requirement Analysis | Manual requirements interpretation | Developer 1 | 2024-04-01 09:15 | 2024-04-01 11:03 | 1.8 | Extract actors, assets, and constraints from seafood scenario; implement core logic (log 2)
Requirement Analysis | Manual requirements interpretation | Developer 2 | 2024-04-01 09:30 | 2024-04-01 11:18 | 1.8 | Extract actors, assets, and constraints from seafood scenario; implement supporting logic (log 3)
Requirement Analysis | Manual requirements interpretation | Tester 1 | 2024-04-01 09:20 | 2024-04-01 09:56 | 0.6 | Extract actors, assets, and constraints from seafood scenario; design/execute tests (log 4)
Requirement Analysis | Manual requirements interpretation | Tester 2 | 2024-04-01 09:30 | 2024-04-01 10:06 | 0.6 | Review seafood traceability brief and draft user stories for Fisher/Retailer; validate/debug tests (log 5)
Requirement Analysis | Model refinement and validation | Project Manager | 2024-04-01 11:28 | 2024-04-01 14:46 | 1.8 | Validate requirement models and update XML specifications; coordinate/review (log 6)
Requirement Analysis | Model refinement and validation | Developer 1 | 2024-04-01 11:28 | 2024-04-01 15:40 | 2.7 | Refine DAOM/BPMN or UML use cases; resolve ambiguities; implement core logic (log 7)
Requirement Analysis | Model refinement and validation | Developer 2 | 2024-04-01 11:33 | 2024-04-01 15:45 | 2.7 | Validate requirement models and update XML specifications; implement supporting logic (log 8)
Requirement Analysis | Model refinement and validation | Tester 1 | 2024-04-01 11:33 | 2024-04-01 13:57 | 0.9 | Validate requirement models and update XML specifications; design/execute tests (log 9)
Requirement Analysis | Model refinement and validation | Tester 2 | 2024-04-01 11:33 | 2024-04-01 13:57 | 0.9 | Refine DAOM/BPMN or UML use cases; resolve ambiguities; validate/debug tests (log 10)
Design | UML modeling | Project Manager | 2024-04-01 15:45 | 2024-04-01 20:21 | 3.6 | Map DAOM roles to UML classes and draft interaction lifelines; coordinate/review (log 11)
Design | UML modeling | Developer 1 | 2024-04-01 16:15 | 2024-04-02 10:39 | 5.4 | Create sequence diagrams with gateway guards for logistics handoff; implement core logic (log 12)
Design | UML modeling | Developer 2 | 2024-04-01 16:15 | 2024-04-02 10:39 | 5.4 | Derive UML class/sequence diagrams for FisherContract and RetailerContract; implement supporting logic (log 13)
Design | UML modeling | Tester 1 | 2024-04-01 16:15 | 2024-04-01 19:03 | 1.8 | Map DAOM roles to UML classes and draft interaction lifelines; design/execute tests (log 14)
Design | UML modeling | Tester 2 | 2024-04-01 16:00 | 2024-04-01 17:48 | 1.8 | Map DAOM roles to UML classes and draft interaction lifelines; validate/debug tests (log 15)
Design | Diagram refinement and consistency | Project Manager | 2024-04-02 10:54 | 2024-04-02 14:48 | 2.4 | Consistency check of diagrams against BPMN alignment; coordinate/review (log 16)
Design | Diagram refinement and consistency | Developer 1 | 2024-04-02 10:39 | 2024-04-02 15:45 | 3.6 | Align UML fragments with BPMN gateways; refine guards; implement core logic (log 17)
Design | Diagram refinement and consistency | Developer 2 | 2024-04-02 10:49 | 2024-04-02 15:55 | 3.6 | Align UML fragments with BPMN gateways; refine guards; implement supporting logic (log 18)
Design | Diagram refinement and consistency | Tester 1 | 2024-04-02 10:59 | 2024-04-02 13:41 | 1.2 | Consistency check of diagrams against BPMN alignment; design/execute tests (log 19)
Design | Diagram refinement and consistency | Tester 2 | 2024-04-02 10:59 | 2024-04-02 13:41 | 1.2 | Align UML fragments with BPMN gateways; refine guards; validate/debug tests (log 20)
Coding | Manual code writing | Project Manager | 2024-04-02 16:10 | 2024-04-03 09:10 | 4 | Handwrite Solidity/Go functions and RBAC checks from UML; coordinate/review (log 21)
Coding | Manual code writing | Developer 1 | 2024-04-02 16:10 | 2024-04-03 11:10 | 6 | Complete manual edits in generated skeletons and add platform glue; implement core logic (log 22)
Coding | Manual code writing | Developer 2 | 2024-04-02 16:15 | 2024-04-03 11:15 | 6 | Complete manual edits in generated skeletons and add platform glue; implement supporting logic (log 23)
Coding | Manual code writing | Tester 1 | 2024-04-02 16:15 | 2024-04-02 19:15 | 2 | Complete manual edits in generated skeletons and add platform glue; design/execute tests (log 24)
Coding | Manual code writing | Tester 2 | 2024-04-02 15:55 | 2024-04-02 17:55 | 2 | Handwrite Solidity/Go functions and RBAC checks from UML; validate/debug tests (log 25)
Coding | Debugging and rework | Project Manager | 2024-04-03 11:30 | 2024-04-03 19:54 | 5.9 | Fix compilation errors and reconcile model-code mismatches; coordinate/review (log 26)
Coding | Debugging and rework | Developer 1 | 2024-04-03 11:45 | 2024-04-04 11:06 | 8.85 | Resolve runtime issues and refactor contracts for correctness; implement core logic (log 27)
Coding | Debugging and rework | Developer 2 | 2024-04-03 11:45 | 2024-04-04 11:06 | 8.85 | Fix compilation errors and reconcile model-code mismatches; implement supporting logic (log 28)
Coding | Debugging and rework | Tester 1 | 2024-04-03 11:30 | 2024-04-03 15:57 | 2.95 | Resolve runtime issues and refactor contracts for correctness; design/execute tests (log 29)
Coding | Debugging and rework | Tester 2 | 2024-04-03 11:35 | 2024-04-03 16:02 | 2.95 | Fix compilation errors and reconcile model-code mismatches; validate/debug tests (log 30)
Testing | Test script design/execution | Project Manager | 2024-04-04 11:16 | 2024-04-04 17:46 | 5 | Write and run test cases for key interactions; coordinate/review (log 31)
Testing | Test script design/execution | Developer 1 | 2024-04-04 11:06 | 2024-04-05 09:06 | 7.5 | Write and run test cases for key interactions; implement core logic (log 32)
Testing | Test script design/execution | Developer 2 | 2024-04-04 11:26 | 2024-04-05 09:26 | 7.5 | Design unit tests for normal/exception paths and emitted events; implement supporting logic (log 33)
Testing | Test script design/execution | Tester 1 | 2024-04-04 11:06 | 2024-04-04 15:06 | 2.5 | Design unit tests for normal/exception paths and emitted events; design/execute tests (log 34)
Testing | Test script design/execution | Tester 2 | 2024-04-04 11:36 | 2024-04-04 15:36 | 2.5 | Write and run test cases for key interactions; validate/debug tests (log 35)
Testing | Test validation and debugging | Project Manager | 2024-04-05 09:41 | 2024-04-05 14:23 | 3.2 | Validate state assertions and event checks on chain; coordinate/review (log 36)
Testing | Test validation and debugging | Developer 1 | 2024-04-05 09:41 | 2024-04-05 15:59 | 4.8 | Tune mocks/stubs and fix flaky tests; implement core logic (log 37)
Testing | Test validation and debugging | Developer 2 | 2024-04-05 09:41 | 2024-04-05 15:59 | 4.8 | Analyze test failures, repair scripts, and rerun regression; implement supporting logic (log 38)
Testing | Test validation and debugging | Tester 1 | 2024-04-05 09:41 | 2024-04-05 11:17 | 1.6 | Validate state assertions and event checks on chain; design/execute tests (log 39)
Testing | Test validation and debugging | Tester 2 | 2024-04-05 09:26 | 2024-04-05 11:02 | 1.6 | Analyze test failures, repair scripts, and rerun regression; validate/debug tests (log 40)
Deployment | Script authoring/setup | Project Manager | 2024-04-05 15:59 | 2024-04-05 19:11 | 2.2 | Prepare Ethereum/Fabric deployment scripts and configs; coordinate/review (log 41)
Deployment | Script authoring/setup | Developer 1 | 2024-04-05 16:19 | 2024-04-05 20:37 | 3.3 | Prepare Ethereum/Fabric deployment scripts and configs; implement core logic (log 42)
Deployment | Script authoring/setup | Developer 2 | 2024-04-05 16:14 | 2024-04-05 20:32 | 3.3 | Prepare Ethereum/Fabric deployment scripts and configs; implement supporting logic (log 43)
Deployment | Script authoring/setup | Tester 1 | 2024-04-05 16:19 | 2024-04-05 17:25 | 1.1 | Prepare Ethereum/Fabric deployment scripts and configs; design/execute tests (log 44)
Deployment | Script authoring/setup | Tester 2 | 2024-04-05 16:09 | 2024-04-05 17:15 | 1.1 | Write Fabric lifecycle commands for Org1/Org2 and seafood channel; validate/debug tests (log 45)
Deployment | Validation and fine-tuning | Project Manager | 2024-04-05 20:52 | 2024-04-06 10:34 | 1.7 | Validate network/contract setup; tune endorsement and ACL; coordinate/review (log 46)
Deployment | Validation and fine-tuning | Developer 1 | 2024-04-05 20:47 | 2024-04-06 11:20 | 2.55 | Perform smoke tests and adjust deployment artifacts; implement core logic (log 47)
Deployment | Validation and fine-tuning | Developer 2 | 2024-04-05 20:57 | 2024-04-06 11:30 | 2.55 | Fix node configuration and rerun deployment; implement supporting logic (log 48)
Deployment | Validation and fine-tuning | Tester 1 | 2024-04-05 20:52 | 2024-04-06 09:43 | 0.85 | Validate network/contract setup; tune endorsement and ACL; design/execute tests (log 49)
Deployment | Validation and fine-tuning | Tester 2 | 2024-04-05 20:52 | 2024-04-06 09:43 | 0.85 | Perform smoke tests and adjust deployment artifacts; validate/debug tests (log 50)

## Framework_Logs
Phase | Sub-task | Role | StartTime | EndTime | Hours | Description
Requirement Analysis | Manual requirements interpretation | Project Manager | 2024-04-06 09:15 | 2024-04-06 10:21 | 1.1 | Review seafood traceability brief and draft user stories for Fisher/Retailer; coordinate/review (log 1)
Requirement Analysis | Manual requirements interpretation | Developer 1 | 2024-04-06 09:00 | 2024-04-06 10:39 | 1.65 | Review seafood traceability brief and draft user stories for Fisher/Retailer; implement core logic (log 2)
Requirement Analysis | Manual requirements interpretation | Developer 2 | 2024-04-06 09:10 | 2024-04-06 10:49 | 1.65 | Review seafood traceability brief and draft user stories for Fisher/Retailer; implement supporting logic (log 3)
Requirement Analysis | Manual requirements interpretation | Tester 1 | 2024-04-06 09:30 | 2024-04-06 10:03 | 0.55 | Extract actors, assets, and constraints from seafood scenario; design/execute tests (log 4)
Requirement Analysis | Manual requirements interpretation | Tester 2 | 2024-04-06 09:00 | 2024-04-06 09:33 | 0.55 | Extract actors, assets, and constraints from seafood scenario; validate/debug tests (log 5)
Requirement Analysis | Model refinement and validation | Project Manager | 2024-04-06 11:09 | 2024-04-06 14:15 | 1.6 | Validate requirement models and update XML specifications; coordinate/review (log 6)
Requirement Analysis | Model refinement and validation | Developer 1 | 2024-04-06 11:09 | 2024-04-06 15:03 | 2.4 | Refine DAOM/BPMN or UML use cases; resolve ambiguities; implement core logic (log 7)
Requirement Analysis | Model refinement and validation | Developer 2 | 2024-04-06 10:59 | 2024-04-06 14:53 | 2.4 | Refine DAOM/BPMN or UML use cases; resolve ambiguities; implement supporting logic (log 8)
Requirement Analysis | Model refinement and validation | Tester 1 | 2024-04-06 11:09 | 2024-04-06 11:57 | 0.8 | Cross-check roles, goals, and message flows for completeness; design/execute tests (log 9)
Requirement Analysis | Model refinement and validation | Tester 2 | 2024-04-06 10:49 | 2024-04-06 11:37 | 0.8 | Refine DAOM/BPMN or UML use cases; resolve ambiguities; validate/debug tests (log 10)
Design | UML modeling | Project Manager | 2024-04-06 15:23 | 2024-04-06 16:47 | 1.4 | Derive UML class/sequence diagrams for FisherContract and RetailerContract; coordinate/review (log 11)
Design | UML modeling | Developer 1 | 2024-04-06 15:18 | 2024-04-06 17:24 | 2.1 | Map DAOM roles to UML classes and draft interaction lifelines; implement core logic (log 12)
Design | UML modeling | Developer 2 | 2024-04-06 15:18 | 2024-04-06 17:24 | 2.1 | Map DAOM roles to UML classes and draft interaction lifelines; implement supporting logic (log 13)
Design | UML modeling | Tester 1 | 2024-04-06 15:18 | 2024-04-06 16:00 | 0.7 | Map DAOM roles to UML classes and draft interaction lifelines; design/execute tests (log 14)
Design | UML modeling | Tester 2 | 2024-04-06 15:13 | 2024-04-06 15:55 | 0.7 | Derive UML class/sequence diagrams for FisherContract and RetailerContract; validate/debug tests (log 15)
Design | Diagram refinement and consistency | Project Manager | 2024-04-06 17:39 | 2024-04-07 09:27 | 2.8 | Consistency check of diagrams against BPMN alignment; coordinate/review (log 16)
Design | Diagram refinement and consistency | Developer 1 | 2024-04-06 17:34 | 2024-04-07 10:46 | 4.2 | Align UML fragments with BPMN gateways; refine guards; implement core logic (log 17)
Design | Diagram refinement and consistency | Developer 2 | 2024-04-06 17:24 | 2024-04-07 10:36 | 4.2 | Review and adjust class attributes and interaction ordering; implement supporting logic (log 18)
Design | Diagram refinement and consistency | Tester 1 | 2024-04-06 17:34 | 2024-04-06 19:58 | 1.4 | Consistency check of diagrams against BPMN alignment; design/execute tests (log 19)
Design | Diagram refinement and consistency | Tester 2 | 2024-04-06 17:34 | 2024-04-06 19:58 | 1.4 | Align UML fragments with BPMN gateways; refine guards; validate/debug tests (log 20)
Coding | Manual code writing | Project Manager | 2024-04-07 11:16 | 2024-04-07 13:46 | 1 | Complete manual edits in generated skeletons and add platform glue; coordinate/review (log 21)
Coding | Manual code writing | Developer 1 | 2024-04-07 11:06 | 2024-04-07 14:06 | 1.5 | Implement recordCatch(), transferBatch(), and event emission logic; implement core logic (log 22)
Coding | Manual code writing | Developer 2 | 2024-04-07 11:16 | 2024-04-07 14:16 | 1.5 | Handwrite Solidity/Go functions and RBAC checks from UML; implement supporting logic (log 23)
Coding | Manual code writing | Tester 1 | 2024-04-07 11:06 | 2024-04-07 11:36 | 0.5 | Implement recordCatch(), transferBatch(), and event emission logic; design/execute tests (log 24)
Coding | Manual code writing | Tester 2 | 2024-04-07 10:46 | 2024-04-07 11:16 | 0.5 | Complete manual edits in generated skeletons and add platform glue; validate/debug tests (log 25)
Coding | Model-based code generation | Project Manager | 2024-04-07 14:46 | 2024-04-07 16:46 | 2 | Regenerate code after parameter tuning and model update; coordinate/review (log 26)
Coding | Model-based code generation | Developer 1 | 2024-04-07 14:16 | 2024-04-07 17:16 | 3 | Run Acceleo generator to produce contract templates; implement core logic (log 27)
Coding | Model-based code generation | Developer 2 | 2024-04-07 14:16 | 2024-04-07 17:16 | 3 | Run Acceleo generator to produce contract templates; implement supporting logic (log 28)
Coding | Model-based code generation | Tester 1 | 2024-04-07 14:46 | 2024-04-07 15:46 | 1 | Regenerate code after parameter tuning and model update; design/execute tests (log 29)
Coding | Model-based code generation | Tester 2 | 2024-04-07 14:16 | 2024-04-07 15:16 | 1 | Execute model-to-code pipeline and inspect generated artifacts; validate/debug tests (log 30)
Coding | Debugging and rework | Project Manager | 2024-04-07 17:16 | 2024-04-08 09:52 | 3.6 | Fix compilation errors and reconcile model-code mismatches; coordinate/review (log 31)
Coding | Debugging and rework | Developer 1 | 2024-04-07 17:36 | 2024-04-08 12:00 | 5.4 | Fix compilation errors and reconcile model-code mismatches; implement core logic (log 32)
Coding | Debugging and rework | Developer 2 | 2024-04-07 17:26 | 2024-04-08 11:50 | 5.4 | Fix compilation errors and reconcile model-code mismatches; implement supporting logic (log 33)
Coding | Debugging and rework | Tester 1 | 2024-04-07 17:31 | 2024-04-07 20:19 | 1.8 | Debug failing transactions; update models/rules accordingly; design/execute tests (log 34)
Coding | Debugging and rework | Tester 2 | 2024-04-07 17:46 | 2024-04-07 20:34 | 1.8 | Resolve runtime issues and refactor contracts for correctness; validate/debug tests (log 35)
Testing | Test script design/execution | Project Manager | 2024-04-08 13:45 | 2024-04-08 15:45 | 2 | Write and run test cases for key interactions; coordinate/review (log 36)
Testing | Test script design/execution | Developer 1 | 2024-04-08 13:50 | 2024-04-08 16:50 | 3 | Generate UML-TP cases and extend with on-chain state oracles; implement core logic (log 37)
Testing | Test script design/execution | Developer 2 | 2024-04-08 14:00 | 2024-04-08 17:00 | 3 | Generate UML-TP cases and extend with on-chain state oracles; implement supporting logic (log 38)
Testing | Test script design/execution | Tester 1 | 2024-04-08 14:00 | 2024-04-08 15:00 | 1 | Design unit tests for normal/exception paths and emitted events; design/execute tests (log 39)
Testing | Test script design/execution | Tester 2 | 2024-04-08 13:45 | 2024-04-08 14:45 | 1 | Write and run test cases for key interactions; validate/debug tests (log 40)
Testing | Test validation and debugging | Project Manager | 2024-04-08 17:00 | 2024-04-09 09:30 | 3.5 | Validate state assertions and event checks on chain; coordinate/review (log 41)
Testing | Test validation and debugging | Developer 1 | 2024-04-08 17:00 | 2024-04-09 11:15 | 5.25 | Validate state assertions and event checks on chain; implement core logic (log 42)
Testing | Test validation and debugging | Developer 2 | 2024-04-08 17:30 | 2024-04-09 11:45 | 5.25 | Validate state assertions and event checks on chain; implement supporting logic (log 43)
Testing | Test validation and debugging | Tester 1 | 2024-04-08 17:10 | 2024-04-08 19:55 | 1.75 | Validate state assertions and event checks on chain; design/execute tests (log 44)
Testing | Test validation and debugging | Tester 2 | 2024-04-08 17:30 | 2024-04-08 20:15 | 1.75 | Tune mocks/stubs and fix flaky tests; validate/debug tests (log 45)
Deployment | Script authoring/setup | Project Manager | 2024-04-09 11:45 | 2024-04-09 14:03 | 0.8 | Parameterize deployment scripts and set initial roles; coordinate/review (log 46)
Deployment | Script authoring/setup | Developer 1 | 2024-04-09 11:45 | 2024-04-09 14:27 | 1.2 | Write Fabric lifecycle commands for Org1/Org2 and seafood channel; implement core logic (log 47)
Deployment | Script authoring/setup | Developer 2 | 2024-04-09 11:45 | 2024-04-09 14:27 | 1.2 | Prepare Ethereum/Fabric deployment scripts and configs; implement supporting logic (log 48)
Deployment | Script authoring/setup | Tester 1 | 2024-04-09 13:30 | 2024-04-09 13:54 | 0.4 | Parameterize deployment scripts and set initial roles; design/execute tests (log 49)
Deployment | Script authoring/setup | Tester 2 | 2024-04-09 11:55 | 2024-04-09 13:49 | 0.4 | Write Fabric lifecycle commands for Org1/Org2 and seafood channel; validate/debug tests (log 50)
Deployment | Validation and fine-tuning | Project Manager | 2024-04-09 14:47 | 2024-04-09 16:47 | 2 | Perform smoke tests and adjust deployment artifacts; coordinate/review (log 51)
Deployment | Validation and fine-tuning | Developer 1 | 2024-04-09 14:47 | 2024-04-09 17:47 | 3 | Fix node configuration and rerun deployment; implement core logic (log 52)
Deployment | Validation and fine-tuning | Developer 2 | 2024-04-09 14:37 | 2024-04-09 17:37 | 3 | Validate network/contract setup; tune endorsement and ACL; implement supporting logic (log 53)
Deployment | Validation and fine-tuning | Tester 1 | 2024-04-09 14:37 | 2024-04-09 15:37 | 1 | Validate network/contract setup; tune endorsement and ACL; design/execute tests (log 54)
Deployment | Validation and fine-tuning | Tester 2 | 2024-04-09 14:47 | 2024-04-09 15:47 | 1 | Fix node configuration and rerun deployment; validate/debug tests (log 55)

## TeamLevel
Group | Phase | StartTime | EndTime | TotalManHours | TeamActivitySummary | Checkpoint
Traditional | Requirement Analysis | 2024-04-01 09:15 | 2024-04-01 15:45 | 15 | Manual requirements interpretation; Model refinement and validation | Checkpoint: Requirement Analysis artifacts reviewed and approved for next phase.
Traditional | Design | 2024-04-01 15:45 | 2024-04-02 15:55 | 30 | UML modeling; Diagram refinement and consistency | Checkpoint: Design artifacts reviewed and approved for next phase.
Traditional | Coding | 2024-04-02 15:55 | 2024-04-04 11:06 | 49.5 | Manual code writing; Model-based code generation; Debugging and rework | Checkpoint: Coding artifacts reviewed and approved for next phase.
Traditional | Testing | 2024-04-04 11:06 | 2024-04-05 15:59 | 41 | Test script design/execution; Test validation and debugging | Checkpoint: Testing artifacts reviewed and approved for next phase.
Traditional | Deployment | 2024-04-05 15:59 | 2024-04-06 11:30 | 19.5 | Script authoring/setup; Validation and fine-tuning | Checkpoint: Deployment artifacts reviewed and approved for next phase.
Framework | Requirement Analysis | 2024-04-06 09:00 | 2024-04-06 15:03 | 13.5 | Manual requirements interpretation; Model refinement and validation | Checkpoint: Requirement Analysis artifacts reviewed and approved for next phase.
Framework | Design | 2024-04-06 15:13 | 2024-04-07 10:46 | 21 | UML modeling; Diagram refinement and consistency | Checkpoint: Design artifacts reviewed and approved for next phase.
Framework | Coding | 2024-04-07 10:46 | 2024-04-08 12:00 | 33 | Manual code writing; Model-based code generation; Debugging and rework | Checkpoint: Coding artifacts reviewed and approved for next phase.
Framework | Testing | 2024-04-08 13:45 | 2024-04-09 11:45 | 27.5 | Test script design/execution; Test validation and debugging | Checkpoint: Testing artifacts reviewed and approved for next phase.
Framework | Deployment | 2024-04-09 11:45 | 2024-04-09 17:47 | 14 | Script authoring/setup; Validation and fine-tuning | Checkpoint: Deployment artifacts reviewed and approved for next phase.

## RoleSummary
Group | Role | TotalHours | PhaseBreakdown | KeyActivities
Traditional | Project Manager | 31 | Requirement Analysis:3.0h; Design:6.0h; Coding:9.9h; Testing:8.2h; Deployment:3.9h | Coding/Debugging and rework(5.9h); Testing/Test script design/execution(5.0h); Coding/Manual code writing(4.0h); Design/UML modeling(3.6h); Testing/Test validation and debugging(3.2h)
Traditional | Developer 1 | 46.5 | Requirement Analysis:4.5h; Design:9.0h; Coding:14.85h; Testing:12.3h; Deployment:5.85h | Coding/Debugging and rework(8.85h); Testing/Test script design/execution(7.5h); Coding/Manual code writing(6.0h); Design/UML modeling(5.4h); Testing/Test validation and debugging(4.8h)
Traditional | Developer 2 | 46.5 | Requirement Analysis:4.5h; Design:9.0h; Coding:14.85h; Testing:12.3h; Deployment:5.85h | Coding/Debugging and rework(8.85h); Testing/Test script design/execution(7.5h); Coding/Manual code writing(6.0h); Design/UML modeling(5.4h); Testing/Test validation and debugging(4.8h)
Traditional | Tester 1 | 15.5 | Requirement Analysis:1.5h; Design:3.0h; Coding:4.95h; Testing:4.1h; Deployment:1.95h | Coding/Debugging and rework(2.95h); Testing/Test script design/execution(2.5h); Coding/Manual code writing(2.0h); Design/UML modeling(1.8h); Testing/Test validation and debugging(1.6h)
Traditional | Tester 2 | 15.5 | Requirement Analysis:1.5h; Design:3.0h; Coding:4.95h; Testing:4.1h; Deployment:1.95h | Coding/Debugging and rework(2.95h); Testing/Test script design/execution(2.5h); Coding/Manual code writing(2.0h); Design/UML modeling(1.8h); Testing/Test validation and debugging(1.6h)
Framework | Project Manager | 21.8 | Requirement Analysis:2.7h; Design:4.2h; Coding:6.6h; Testing:5.5h; Deployment:2.8h | Coding/Debugging and rework(3.6h); Testing/Test validation and debugging(3.5h); Design/Diagram refinement and consistency(2.8h); Coding/Model-based code generation(2.0h); Testing/Test script design/execution(2.0h)
Framework | Developer 1 | 32.7 | Requirement Analysis:4.05h; Design:6.3h; Coding:9.9h; Testing:8.25h; Deployment:4.2h | Coding/Debugging and rework(5.4h); Testing/Test validation and debugging(5.25h); Design/Diagram refinement and consistency(4.2h); Coding/Model-based code generation(3.0h); Testing/Test script design/execution(3.0h)
Framework | Developer 2 | 32.7 | Requirement Analysis:4.05h; Design:6.3h; Coding:9.9h; Testing:8.25h; Deployment:4.2h | Coding/Debugging and rework(5.4h); Testing/Test validation and debugging(5.25h); Design/Diagram refinement and consistency(4.2h); Coding/Model-based code generation(3.0h); Testing/Test script design/execution(3.0h)
Framework | Tester 1 | 10.9 | Requirement Analysis:1.35h; Design:2.1h; Coding:3.3h; Testing:2.75h; Deployment:1.4h | Coding/Debugging and rework(1.8h); Testing/Test validation and debugging(1.75h); Design/Diagram refinement and consistency(1.4h); Coding/Model-based code generation(1.0h); Testing/Test script design/execution(1.0h)
Framework | Tester 2 | 10.9 | Requirement Analysis:1.35h; Design:2.1h; Coding:3.3h; Testing:2.75h; Deployment:1.4h | Coding/Debugging and rework(1.8h); Testing/Test validation and debugging(1.75h); Design/Diagram refinement and consistency(1.4h); Coding/Model-based code generation(1.0h); Testing/Test script design/execution(1.0h)

## IndividualSchedule
Group | Person | Date | StartTime | EndTime | Hours | Phase | Sub-task | Description
Traditional | Project Manager | 2024-04-01 | 09:20 | 10:32 | 1.2 | Requirement Analysis | Manual requirements interpretation | Review seafood traceability brief and draft user stories for Fisher/Retailer; coordinate/review (log 1)
Traditional | Developer 1 | 2024-04-01 | 09:15 | 11:03 | 1.8 | Requirement Analysis | Manual requirements interpretation | Extract actors, assets, and constraints from seafood scenario; implement core logic (log 2)
Traditional | Developer 2 | 2024-04-01 | 09:30 | 11:18 | 1.8 | Requirement Analysis | Manual requirements interpretation | Extract actors, assets, and constraints from seafood scenario; implement supporting logic (log 3)
Traditional | Tester 1 | 2024-04-01 | 09:20 | 09:56 | 0.6 | Requirement Analysis | Manual requirements interpretation | Extract actors, assets, and constraints from seafood scenario; design/execute tests (log 4)
Traditional | Tester 2 | 2024-04-01 | 09:30 | 10:06 | 0.6 | Requirement Analysis | Manual requirements interpretation | Review seafood traceability brief and draft user stories for Fisher/Retailer; validate/debug tests (log 5)
Traditional | Project Manager | 2024-04-01 | 11:28 | 14:46 | 1.8 | Requirement Analysis | Model refinement and validation | Validate requirement models and update XML specifications; coordinate/review (log 6)
Traditional | Developer 1 | 2024-04-01 | 11:28 | 15:40 | 2.7 | Requirement Analysis | Model refinement and validation | Refine DAOM/BPMN or UML use cases; resolve ambiguities; implement core logic (log 7)
Traditional | Developer 2 | 2024-04-01 | 11:33 | 15:45 | 2.7 | Requirement Analysis | Model refinement and validation | Validate requirement models and update XML specifications; implement supporting logic (log 8)
Traditional | Tester 1 | 2024-04-01 | 11:33 | 13:57 | 0.9 | Requirement Analysis | Model refinement and validation | Validate requirement models and update XML specifications; design/execute tests (log 9)
Traditional | Tester 2 | 2024-04-01 | 11:33 | 13:57 | 0.9 | Requirement Analysis | Model refinement and validation | Refine DAOM/BPMN or UML use cases; resolve ambiguities; validate/debug tests (log 10)
Traditional | Project Manager | 2024-04-01 | 15:45 | 20:21 | 3.6 | Design | UML modeling | Map DAOM roles to UML classes and draft interaction lifelines; coordinate/review (log 11)
Traditional | Developer 1 | 2024-04-01 | 16:15 | 10:39 | 5.4 | Design | UML modeling | Create sequence diagrams with gateway guards for logistics handoff; implement core logic (log 12)
Traditional | Developer 2 | 2024-04-01 | 16:15 | 10:39 | 5.4 | Design | UML modeling | Derive UML class/sequence diagrams for FisherContract and RetailerContract; implement supporting logic (log 13)
Traditional | Tester 1 | 2024-04-01 | 16:15 | 19:03 | 1.8 | Design | UML modeling | Map DAOM roles to UML classes and draft interaction lifelines; design/execute tests (log 14)
Traditional | Tester 2 | 2024-04-01 | 16:00 | 17:48 | 1.8 | Design | UML modeling | Map DAOM roles to UML classes and draft interaction lifelines; validate/debug tests (log 15)
Traditional | Project Manager | 2024-04-02 | 10:54 | 14:48 | 2.4 | Design | Diagram refinement and consistency | Consistency check of diagrams against BPMN alignment; coordinate/review (log 16)
Traditional | Developer 1 | 2024-04-02 | 10:39 | 15:45 | 3.6 | Design | Diagram refinement and consistency | Align UML fragments with BPMN gateways; refine guards; implement core logic (log 17)
Traditional | Developer 2 | 2024-04-02 | 10:49 | 15:55 | 3.6 | Design | Diagram refinement and consistency | Align UML fragments with BPMN gateways; refine guards; implement supporting logic (log 18)
Traditional | Tester 1 | 2024-04-02 | 10:59 | 13:41 | 1.2 | Design | Diagram refinement and consistency | Consistency check of diagrams against BPMN alignment; design/execute tests (log 19)
Traditional | Tester 2 | 2024-04-02 | 10:59 | 13:41 | 1.2 | Design | Diagram refinement and consistency | Align UML fragments with BPMN gateways; refine guards; validate/debug tests (log 20)
Traditional | Project Manager | 2024-04-02 | 16:10 | 09:10 | 4 | Coding | Manual code writing | Handwrite Solidity/Go functions and RBAC checks from UML; coordinate/review (log 21)
Traditional | Developer 1 | 2024-04-02 | 16:10 | 11:10 | 6 | Coding | Manual code writing | Complete manual edits in generated skeletons and add platform glue; implement core logic (log 22)
Traditional | Developer 2 | 2024-04-02 | 16:15 | 11:15 | 6 | Coding | Manual code writing | Complete manual edits in generated skeletons and add platform glue; implement supporting logic (log 23)
Traditional | Tester 1 | 2024-04-02 | 16:15 | 19:15 | 2 | Coding | Manual code writing | Complete manual edits in generated skeletons and add platform glue; design/execute tests (log 24)
Traditional | Tester 2 | 2024-04-02 | 15:55 | 17:55 | 2 | Coding | Manual code writing | Handwrite Solidity/Go functions and RBAC checks from UML; validate/debug tests (log 25)
Traditional | Project Manager | 2024-04-03 | 11:30 | 19:54 | 5.9 | Coding | Debugging and rework | Fix compilation errors and reconcile model-code mismatches; coordinate/review (log 26)
Traditional | Developer 1 | 2024-04-03 | 11:45 | 11:06 | 8.85 | Coding | Debugging and rework | Resolve runtime issues and refactor contracts for correctness; implement core logic (log 27)
Traditional | Developer 2 | 2024-04-03 | 11:45 | 11:06 | 8.85 | Coding | Debugging and rework | Fix compilation errors and reconcile model-code mismatches; implement supporting logic (log 28)
Traditional | Tester 1 | 2024-04-03 | 11:30 | 15:57 | 2.95 | Coding | Debugging and rework | Resolve runtime issues and refactor contracts for correctness; design/execute tests (log 29)
Traditional | Tester 2 | 2024-04-03 | 11:35 | 16:02 | 2.95 | Coding | Debugging and rework | Fix compilation errors and reconcile model-code mismatches; validate/debug tests (log 30)
Traditional | Project Manager | 2024-04-04 | 11:16 | 17:46 | 5 | Testing | Test script design/execution | Write and run test cases for key interactions; coordinate/review (log 31)
Traditional | Developer 1 | 2024-04-04 | 11:06 | 09:06 | 7.5 | Testing | Test script design/execution | Write and run test cases for key interactions; implement core logic (log 32)
Traditional | Developer 2 | 2024-04-04 | 11:26 | 09:26 | 7.5 | Testing | Test script design/execution | Design unit tests for normal/exception paths and emitted events; implement supporting logic (log 33)
Traditional | Tester 1 | 2024-04-04 | 11:06 | 15:06 | 2.5 | Testing | Test script design/execution | Design unit tests for normal/exception paths and emitted events; design/execute tests (log 34)
Traditional | Tester 2 | 2024-04-04 | 11:36 | 15:36 | 2.5 | Testing | Test script design/execution | Write and run test cases for key interactions; validate/debug tests (log 35)
Traditional | Project Manager | 2024-04-05 | 09:41 | 14:23 | 3.2 | Testing | Test validation and debugging | Validate state assertions and event checks on chain; coordinate/review (log 36)
Traditional | Developer 1 | 2024-04-05 | 09:41 | 15:59 | 4.8 | Testing | Test validation and debugging | Tune mocks/stubs and fix flaky tests; implement core logic (log 37)
Traditional | Developer 2 | 2024-04-05 | 09:41 | 15:59 | 4.8 | Testing | Test validation and debugging | Analyze test failures, repair scripts, and rerun regression; implement supporting logic (log 38)
Traditional | Tester 1 | 2024-04-05 | 09:41 | 11:17 | 1.6 | Testing | Test validation and debugging | Validate state assertions and event checks on chain; design/execute tests (log 39)
Traditional | Tester 2 | 2024-04-05 | 09:26 | 11:02 | 1.6 | Testing | Test validation and debugging | Analyze test failures, repair scripts, and rerun regression; validate/debug tests (log 40)
Traditional | Project Manager | 2024-04-05 | 15:59 | 19:11 | 2.2 | Deployment | Script authoring/setup | Prepare Ethereum/Fabric deployment scripts and configs; coordinate/review (log 41)
Traditional | Developer 1 | 2024-04-05 | 16:19 | 20:37 | 3.3 | Deployment | Script authoring/setup | Prepare Ethereum/Fabric deployment scripts and configs; implement core logic (log 42)
Traditional | Developer 2 | 2024-04-05 | 16:14 | 20:32 | 3.3 | Deployment | Script authoring/setup | Prepare Ethereum/Fabric deployment scripts and configs; implement supporting logic (log 43)
Traditional | Tester 1 | 2024-04-05 | 16:19 | 17:25 | 1.1 | Deployment | Script authoring/setup | Prepare Ethereum/Fabric deployment scripts and configs; design/execute tests (log 44)
Traditional | Tester 2 | 2024-04-05 | 16:09 | 17:15 | 1.1 | Deployment | Script authoring/setup | Write Fabric lifecycle commands for Org1/Org2 and seafood channel; validate/debug tests (log 45)
Traditional | Project Manager | 2024-04-05 | 20:52 | 10:34 | 1.7 | Deployment | Validation and fine-tuning | Validate network/contract setup; tune endorsement and ACL; coordinate/review (log 46)
Traditional | Developer 1 | 2024-04-05 | 20:47 | 11:20 | 2.55 | Deployment | Validation and fine-tuning | Perform smoke tests and adjust deployment artifacts; implement core logic (log 47)
Traditional | Developer 2 | 2024-04-05 | 20:57 | 11:30 | 2.55 | Deployment | Validation and fine-tuning | Fix node configuration and rerun deployment; implement supporting logic (log 48)
Traditional | Tester 1 | 2024-04-05 | 20:52 | 09:43 | 0.85 | Deployment | Validation and fine-tuning | Validate network/contract setup; tune endorsement and ACL; design/execute tests (log 49)
Traditional | Tester 2 | 2024-04-05 | 20:52 | 09:43 | 0.85 | Deployment | Validation and fine-tuning | Perform smoke tests and adjust deployment artifacts; validate/debug tests (log 50)
Framework | Project Manager | 2024-04-06 | 09:15 | 10:21 | 1.1 | Requirement Analysis | Manual requirements interpretation | Review seafood traceability brief and draft user stories for Fisher/Retailer; coordinate/review (log 1)
Framework | Developer 1 | 2024-04-06 | 09:00 | 10:39 | 1.65 | Requirement Analysis | Manual requirements interpretation | Review seafood traceability brief and draft user stories for Fisher/Retailer; implement core logic (log 2)
Framework | Developer 2 | 2024-04-06 | 09:10 | 10:49 | 1.65 | Requirement Analysis | Manual requirements interpretation | Review seafood traceability brief and draft user stories for Fisher/Retailer; implement supporting logic (log 3)
Framework | Tester 1 | 2024-04-06 | 09:30 | 10:03 | 0.55 | Requirement Analysis | Manual requirements interpretation | Extract actors, assets, and constraints from seafood scenario; design/execute tests (log 4)
Framework | Tester 2 | 2024-04-06 | 09:00 | 09:33 | 0.55 | Requirement Analysis | Manual requirements interpretation | Extract actors, assets, and constraints from seafood scenario; validate/debug tests (log 5)
Framework | Project Manager | 2024-04-06 | 11:09 | 14:15 | 1.6 | Requirement Analysis | Model refinement and validation | Validate requirement models and update XML specifications; coordinate/review (log 6)
Framework | Developer 1 | 2024-04-06 | 11:09 | 15:03 | 2.4 | Requirement Analysis | Model refinement and validation | Refine DAOM/BPMN or UML use cases; resolve ambiguities; implement core logic (log 7)
Framework | Developer 2 | 2024-04-06 | 10:59 | 14:53 | 2.4 | Requirement Analysis | Model refinement and validation | Refine DAOM/BPMN or UML use cases; resolve ambiguities; implement supporting logic (log 8)
Framework | Tester 1 | 2024-04-06 | 11:09 | 11:57 | 0.8 | Requirement Analysis | Model refinement and validation | Cross-check roles, goals, and message flows for completeness; design/execute tests (log 9)
Framework | Tester 2 | 2024-04-06 | 10:49 | 11:37 | 0.8 | Requirement Analysis | Model refinement and validation | Refine DAOM/BPMN or UML use cases; resolve ambiguities; validate/debug tests (log 10)
Framework | Project Manager | 2024-04-06 | 15:23 | 16:47 | 1.4 | Design | UML modeling | Derive UML class/sequence diagrams for FisherContract and RetailerContract; coordinate/review (log 11)
Framework | Developer 1 | 2024-04-06 | 15:18 | 17:24 | 2.1 | Design | UML modeling | Map DAOM roles to UML classes and draft interaction lifelines; implement core logic (log 12)
Framework | Developer 2 | 2024-04-06 | 15:18 | 17:24 | 2.1 | Design | UML modeling | Map DAOM roles to UML classes and draft interaction lifelines; implement supporting logic (log 13)
Framework | Tester 1 | 2024-04-06 | 15:18 | 16:00 | 0.7 | Design | UML modeling | Map DAOM roles to UML classes and draft interaction lifelines; design/execute tests (log 14)
Framework | Tester 2 | 2024-04-06 | 15:13 | 15:55 | 0.7 | Design | UML modeling | Derive UML class/sequence diagrams for FisherContract and RetailerContract; validate/debug tests (log 15)
Framework | Project Manager | 2024-04-06 | 17:39 | 09:27 | 2.8 | Design | Diagram refinement and consistency | Consistency check of diagrams against BPMN alignment; coordinate/review (log 16)
Framework | Developer 1 | 2024-04-06 | 17:34 | 10:46 | 4.2 | Design | Diagram refinement and consistency | Align UML fragments with BPMN gateways; refine guards; implement core logic (log 17)
Framework | Developer 2 | 2024-04-06 | 17:24 | 10:36 | 4.2 | Design | Diagram refinement and consistency | Review and adjust class attributes and interaction ordering; implement supporting logic (log 18)
Framework | Tester 1 | 2024-04-06 | 17:34 | 19:58 | 1.4 | Design | Diagram refinement and consistency | Consistency check of diagrams against BPMN alignment; design/execute tests (log 19)
Framework | Tester 2 | 2024-04-06 | 17:34 | 19:58 | 1.4 | Design | Diagram refinement and consistency | Align UML fragments with BPMN gateways; refine guards; validate/debug tests (log 20)
Framework | Project Manager | 2024-04-07 | 11:16 | 13:46 | 1 | Coding | Manual code writing | Complete manual edits in generated skeletons and add platform glue; coordinate/review (log 21)
Framework | Developer 1 | 2024-04-07 | 11:06 | 14:06 | 1.5 | Coding | Manual code writing | Implement recordCatch(), transferBatch(), and event emission logic; implement core logic (log 22)
Framework | Developer 2 | 2024-04-07 | 11:16 | 14:16 | 1.5 | Coding | Manual code writing | Handwrite Solidity/Go functions and RBAC checks from UML; implement supporting logic (log 23)
Framework | Tester 1 | 2024-04-07 | 11:06 | 11:36 | 0.5 | Coding | Manual code writing | Implement recordCatch(), transferBatch(), and event emission logic; design/execute tests (log 24)
Framework | Tester 2 | 2024-04-07 | 10:46 | 11:16 | 0.5 | Coding | Manual code writing | Complete manual edits in generated skeletons and add platform glue; validate/debug tests (log 25)
Framework | Project Manager | 2024-04-07 | 14:46 | 16:46 | 2 | Coding | Model-based code generation | Regenerate code after parameter tuning and model update; coordinate/review (log 26)
Framework | Developer 1 | 2024-04-07 | 14:16 | 17:16 | 3 | Coding | Model-based code generation | Run Acceleo generator to produce contract templates; implement core logic (log 27)
Framework | Developer 2 | 2024-04-07 | 14:16 | 17:16 | 3 | Coding | Model-based code generation | Run Acceleo generator to produce contract templates; implement supporting logic (log 28)
Framework | Tester 1 | 2024-04-07 | 14:46 | 15:46 | 1 | Coding | Model-based code generation | Regenerate code after parameter tuning and model update; design/execute tests (log 29)
Framework | Tester 2 | 2024-04-07 | 14:16 | 15:16 | 1 | Coding | Model-based code generation | Execute model-to-code pipeline and inspect generated artifacts; validate/debug tests (log 30)
Framework | Project Manager | 2024-04-07 | 17:16 | 09:52 | 3.6 | Coding | Debugging and rework | Fix compilation errors and reconcile model-code mismatches; coordinate/review (log 31)
Framework | Developer 1 | 2024-04-07 | 17:36 | 12:00 | 5.4 | Coding | Debugging and rework | Fix compilation errors and reconcile model-code mismatches; implement core logic (log 32)
Framework | Developer 2 | 2024-04-07 | 17:26 | 11:50 | 5.4 | Coding | Debugging and rework | Fix compilation errors and reconcile model-code mismatches; implement supporting logic (log 33)
Framework | Tester 1 | 2024-04-07 | 17:31 | 20:19 | 1.8 | Coding | Debugging and rework | Debug failing transactions; update models/rules accordingly; design/execute tests (log 34)
Framework | Tester 2 | 2024-04-07 | 17:46 | 20:34 | 1.8 | Coding | Debugging and rework | Resolve runtime issues and refactor contracts for correctness; validate/debug tests (log 35)
Framework | Project Manager | 2024-04-08 | 13:45 | 15:45 | 2 | Testing | Test script design/execution | Write and run test cases for key interactions; coordinate/review (log 36)
Framework | Developer 1 | 2024-04-08 | 13:50 | 16:50 | 3 | Testing | Test script design/execution | Generate UML-TP cases and extend with on-chain state oracles; implement core logic (log 37)
Framework | Developer 2 | 2024-04-08 | 14:00 | 17:00 | 3 | Testing | Test script design/execution | Generate UML-TP cases and extend with on-chain state oracles; implement supporting logic (log 38)
Framework | Tester 1 | 2024-04-08 | 14:00 | 15:00 | 1 | Testing | Test script design/execution | Design unit tests for normal/exception paths and emitted events; design/execute tests (log 39)
Framework | Tester 2 | 2024-04-08 | 13:45 | 14:45 | 1 | Testing | Test script design/execution | Write and run test cases for key interactions; validate/debug tests (log 40)
Framework | Project Manager | 2024-04-08 | 17:00 | 09:30 | 3.5 | Testing | Test validation and debugging | Validate state assertions and event checks on chain; coordinate/review (log 41)
Framework | Developer 1 | 2024-04-08 | 17:00 | 11:15 | 5.25 | Testing | Test validation and debugging | Validate state assertions and event checks on chain; implement core logic (log 42)
Framework | Developer 2 | 2024-04-08 | 17:30 | 11:45 | 5.25 | Testing | Test validation and debugging | Validate state assertions and event checks on chain; implement supporting logic (log 43)
Framework | Tester 1 | 2024-04-08 | 17:10 | 19:55 | 1.75 | Testing | Test validation and debugging | Validate state assertions and event checks on chain; design/execute tests (log 44)
Framework | Tester 2 | 2024-04-08 | 17:30 | 20:15 | 1.75 | Testing | Test validation and debugging | Tune mocks/stubs and fix flaky tests; validate/debug tests (log 45)
Framework | Project Manager | 2024-04-09 | 11:45 | 14:03 | 0.8 | Deployment | Script authoring/setup | Parameterize deployment scripts and set initial roles; coordinate/review (log 46)
Framework | Developer 1 | 2024-04-09 | 11:45 | 14:27 | 1.2 | Deployment | Script authoring/setup | Write Fabric lifecycle commands for Org1/Org2 and seafood channel; implement core logic (log 47)
Framework | Developer 2 | 2024-04-09 | 11:45 | 14:27 | 1.2 | Deployment | Script authoring/setup | Prepare Ethereum/Fabric deployment scripts and configs; implement supporting logic (log 48)
Framework | Tester 1 | 2024-04-09 | 13:30 | 13:54 | 0.4 | Deployment | Script authoring/setup | Parameterize deployment scripts and set initial roles; design/execute tests (log 49)
Framework | Tester 2 | 2024-04-09 | 11:55 | 13:49 | 0.4 | Deployment | Script authoring/setup | Write Fabric lifecycle commands for Org1/Org2 and seafood channel; validate/debug tests (log 50)
Framework | Project Manager | 2024-04-09 | 14:47 | 16:47 | 2 | Deployment | Validation and fine-tuning | Perform smoke tests and adjust deployment artifacts; coordinate/review (log 51)
Framework | Developer 1 | 2024-04-09 | 14:47 | 17:47 | 3 | Deployment | Validation and fine-tuning | Fix node configuration and rerun deployment; implement core logic (log 52)
Framework | Developer 2 | 2024-04-09 | 14:37 | 17:37 | 3 | Deployment | Validation and fine-tuning | Validate network/contract setup; tune endorsement and ACL; implement supporting logic (log 53)
Framework | Tester 1 | 2024-04-09 | 14:37 | 15:37 | 1 | Deployment | Validation and fine-tuning | Validate network/contract setup; tune endorsement and ACL; design/execute tests (log 54)
Framework | Tester 2 | 2024-04-09 | 14:47 | 15:47 | 1 | Deployment | Validation and fine-tuning | Fix node configuration and rerun deployment; validate/debug tests (log 55)